## Slide 1
2022 YTD Vendor
Payment Inquiry
Tim Enfield
February 3, 2023
Case Study Review
8:30 AM CST

## Slide 2
Background and Assumptions
Data Takeaways
Implications and Next Steps
Q&A
Agenda: How We Will Spend This Hour
Set the stage with the core business need to examine the ~2900 purchase orders in process so far in 2022. (5 min.)
Focus on processing times, staffing, and vendor outlooks, with an eye of outliers and potential areas of concern. (30 min.)
Translating the core data takeaways into business considerations and processes to review (10 min)
What Needs Clarification? (15 min.)
February 3, 2023
Case Study Review
8:30 AM CST

## Slide 3
Background and Assumptions
(5 min)
Business Ask: Measure and Assess Work Completion and Payment Approval for vendors during the first part of 2022.
February 3, 2023
Case Study Review
8:30 AM CST
Primary Objectives:
  Understand when completed work is being paid, compared to 7-day goal turnaround
  Explore staffing needs and expectations for process owners (Project Coordinators and Specialists)
  Additionally, identify any data gaps that might shed light on process improvements
Data Details:
Purchase Order data aggregated from 1/1/2022 to 2/28/22 (most recent available) based on invoice data, employee records, and a list from Project Services about when work was delivered.
2901 unique POs/Jobs listed, as a combination of in process, completed, paid, and unpaid efforts.
Data Assumptions:
Power BI Desktop was used due to license limitation – if presented, presentation would be linked into this report.
Snapshot Data: Today’s Date is 3/1/22 (parameter will be used to alter if needed). Less Longtidunal Benefit for date filter given only 2 months.
Goal Turnaround: 7 calendar (and not business) days. SLA is merely an internal, non-contractual metric at this time, used for ease of use.
Age: can be defined as days since project completion. Capped at 58 days since no completion date dates prior to 2022 are in data set. Assumption is that all POs opened in 2022 and no carry over occurred.

## Slide 4
Data Takeaways
(30 min)
What the Numbers Tell Us
February 3, 2023
Case Study Review
8:30 AM CST
Key Findings | Considerations
Theme: Project Closure/Payment Timing: Majority of open jobs have not completed and therefore not ready to be paid (63%). 56% of Completed Projects have payment approved within 7 days, independent of whether a Blanket or Standard PO was used. Nearly 70% of Completed Projects are approved within 2 weeks. 88% of Completed Projects are approved within 1 month. The companies’ largest vendors (Tucson, Diablo) have the most open POs and the lowest SLAs. | What is an expected turnaround for a
Theme: Staffing and Roles Impact: The 815 open Purchase Orders are not evenly distributed amongst the 100 staff. Some staff are taking as much as 10% of the overall PO workload, many <1%. A few staff members with very large assignment numbers have predominantly “Unapproved” POs. Project Coordinators have incorrectly handled 954 of 2255 (42%) blanket POs. 80 Project Coordinators average 5 Open POs assigned, while the 20 specialist have 21 assigned on average. | Coordinators and Specialist
Refer to the related “Vendor Payment” Power BI Report. [GITHUB DOWNLOAD]
Notes: Other Interesting Findings
An average invoice/PO is $600 and 2 the two largest vendors account for 61% of POs
During the two months reviewed, processing outpaced work completion velocity, but in the last 2 weeks of February there was a noted spike in work entering and exiting the queue.

## Slide 5
Implications and Next Steps
(10 min)
Exploring the Business Opportunities
February 3, 2023
Case Study Review
8:30 AM CST
Exploring the Business Opportunities to Improve SLA % and Overall Efficiency
Opportunity #1: Review PO Staffing Workloads and Allocations, specifically with Blanket POs Project Coordinators and Project Specialists may be able to share work more effectively, adjust resourcing needs. Next Step: Meet with managers to better align allocation processes and training for each role. Opportunity #2: Explore PO Review Cycles to Understand Large Volume of Open POs Invoices are paid from incomplete projects, and overwhelming number of incomplete projects have open POs. Next Step: Discuss with Project teams what reviews can be added to review PO backlog periodically. Opportunity #3: Increase Visibility to the Largest Vendors The largest vendors need to be served better once their work is completed. Next Step: Discuss with Procurement and A/P what additional alerts or support can be provided. Opportunity #4: Understand Increased Volume in late February Will it be the new normal or just an anomaly? Next Step: Expand review into past years, if available, and explore any seasonality/trends. Ensure forecasts are visible for appropriate managers.
Potential Areas of Data Concern (see ‘Records to Review’ page): “Project Not Completed”, but Paid Invoices Large # of POs opened, but not work yet completed Largest Vendor Volume, Lowest SLA Coordinator vs. Specialist Staffing Levels/Responsibilities Spike in February Volume

## Slide 6
Q&A
(15 min)
This is just meant as the launching point for a broader conversation.
February 3, 2023
Case Study Review
8:30 AM CST
What sparked your interest?

## Slide 7
Q&A
(15 min)
TIM ENFIELD
For Further Considerations
BI Reporting Analyst II
(505) 470-3296
timothypenfield@gmail.com
February 3, 2023
Case Study Review
8:30 AM CST